## Summary
Way of working | Scrum team
Phases | Backlog → Sprint → After the sprint
Stages | 6
Gates | 2
Roles | PO, SM, DEV
To look at | Nothing to look at

## Stages
# | id | Phase | Stage | Led by | Take part | Key question | Comes in | Delivers | Metrics | Activities | Where | Limit | Description
1 | capture | Backlog | Capture | Product | PO | Who asked for it, and why? | Requests from users and stakeholders (from outside) | Backlog item with its why | Items captured per sprint
2 | refine | Backlog | Refine | Development team | DEV, PO | Do we understand it well enough to size it? | Backlog item with its why (Capture) | Acceptance criteria; Estimate | % of items ready before planning
3 | build | Sprint | Build | Development team | DEV, SM | Does it meet the acceptance criteria? | Item ready for a sprint (Ready for a sprint?) | Increment that works | Cycle time | Code review by a second developer |  | 3
4 | accept | Sprint | Accept | Product | PO | Is it what was asked? | Increment that works (Build); Acceptance criteria (Refine) | Item accepted | % accepted at first review
5 | release | After the sprint | Release | Development team | DEV | Is it in the hands of users? | Done item (Done?) | Release notes | Release frequency
6 | measure | After the sprint | Measure the outcome | Product | PO | Did it change what we hoped? | Release notes (Release) | The number two weeks later | Outcome against target

## Gates
id | Gate | After | Approves | Criteria | If it fails | What comes out | Metrics | Results
ready | Ready for a sprint? | Refine | DEV | Outputs: Acceptance criteria, Estimate | Refine | Item ready for a sprint | % ready at first review | Ready / Not yet
done | Done? | Accept | PO | Outputs: Increment that works, Item accepted Activities of «Build» done | Build | Done item | Items done per sprint | Done / Back to build

## Roles (RACI)
Role | Name | Led by | Capture | Refine | Build | Accept | Release | Measure the outcome
PO | Product Owner | Product | R | C |  | R/A |  | R
SM | Scrum Master | Development team |  |  | R
DEV | Developers | Development team |  | R/A | R |  | R
R leads (the stage’s lane) · C takes part · A approves the gate after it

## Outputs
Stage | id | Output | Description | By | KPI
Capture | item | Backlog item with its why
Refine | criteria | Acceptance criteria
Refine | estimate | Estimate
Build | increment | Increment that works
Accept | accepted | Item accepted
Release | notes | Release notes
Measure the outcome | outcome | The number two weeks later |  |  | yes

## KPIs
id | Name | Unit | Stage | Source | Since

## Gate checklist
Gate | What must be ready | Who confirms | OK? | Note
Ready for a sprint? | ☐ Acceptance criteria | DEV
| ☐ Estimate | DEV
Done? | ☐ Increment that works | PO
| ☐ Item accepted | PO
| ☐ Activities of «Build» done | PO

## Thread
From | Output | To
Capture | Backlog item with its why | Refine
Refine | Acceptance criteria | Ready for a sprint?; Accept
Refine | Estimate | Ready for a sprint?
Ready for a sprint? | Item ready for a sprint | Build
Build | Increment that works | Accept; Done?
Accept | Item accepted | Done?
Done? | Done item | Release
Release | Release notes | Measure the outcome
Measure the outcome | The number two weeks later | (nobody)
(from outside) | Requests from users and stakeholders | Capture